## Hoja1
caitan |  | zzz | ADMINISTRADOR | caitan | zz | JEFE OFICINA TECNICA | caitan | zzz | JEFE DE TERRENO | NOMBRE DE EMPRESA MANDANTE | NOMBRE DEL ITO | ITO APROBADOR
INGENIERO ADMINISTRADOR |  | zzz | JEFE OFICINA TECNICA | zzz | ING. CONTROL INGENIERÍA | zz | PLANIFICADOR | zzz | PROGRAMADOR | zzz | CONTROL COSTO | zzz | PREV. SERNAGEOMIN B | zzz | PREVENCIONISTA SNS | zzz | JEFE GESTION CALIDAD | zzz | INSPECTOR DE CALIDAD | zzz | JEFE DE TERRENO | zzz | ING. PUESTA EN MARCHA | zzz | SUPERVISOR CIVIL | zzz | SUPERVISOR ESTRUCTURA | zzz | SUPERVISOR PIPING - DUCTOS | zzz | SUPERVISOR ELÉC./INSTRUM. | zzz | DIBUJANTE ISOMETRISTA | zzz | ACTIVADOR DE MATERIALES | zzz | PAÑOLERO | zzz | ADMINISTRATIVO | zzz | ENCARGADO COMPRAS Y LOGISTICA | zzz | TOPÓGRAFO | zzz
Area | Esp |  | Item | Descripción | Descripción2 | Rol de especialidad | Unid | Cant | Rend | N° Trabajadores | Trabajo | Duración | Comienzo Programado | Fin Programado | time axis 2019-11-01 to 2020-07-07
Sea Water Intake (SWI) | Machanical Test | mecanico@lekapp.cl | IT-10101 | Marine Works | Intake Tower |  |  | 1 |  | 1 | 76.2857 | 0
[6 empty] | Lubrication Complete | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Final Alignement | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Functional Test Protective Devices | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | DCS Permisives And Interlocks Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Functional Test Open/Close (L/R) | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Check / Adjust Position Limits | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Operational / Functional Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Hydrostatic Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Neumatical Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Visual Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Tightntss Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Check Cathodic Protection Complete | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Charger Gas | [6 empty] | 2019-11-29 | 2020-02-16
Sea Water Intake (SWI) | Test Control Valves | mecanico@lekapp.cl | IT-10101 | Marine Works | Intake Tower
[6 empty] | DCS Permisives And Interlocks Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Functional Test Open/Close (L/R) | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Functional And Stroke Test (DCS) | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Check / Adjust Position Limits (Torque) | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Verify Local Indication | [6 empty] | 2019-11-29 | 2020-02-16
Sea Water Intake (SWI) | Test Valves (M) | mecanico@lekapp.cl | IT-10101 | Marine Works | Intake Tower
[6 empty] | No Leakage Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Signal Test To DCS | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Check / Adjust Position Limits | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Check Local Indicator | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | DCS Permisives And Interlocks Test | [6 empty] | 2019-11-29 | 2020-02-16
Sea Water Intake (SWI) | Test Instruments | mecanico@lekapp.cl | IT-10101 | Marine Works | Intake Tower
[6 empty] | Signal Test To DCS | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Check Ranges And Process (Var) | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | DCS Permisives And Interlocks Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Check Ranges And Process (Var) | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Check And Adjust Rangers O/C | [6 empty] | 2019-11-29 | 2020-02-16
Sea Water Intake (SWI) | Motor Test | mecanico@lekapp.cl | IT-10101 | Marine Works | Intake Tower
[6 empty] | Lubrication Complete | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Insulation Resistance Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Winding Resistance Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Polarity Index Measure | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Rotate Direction Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Rotate Test (Variable Measurement) | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | DCS Permisives And Interlocks Test | [6 empty] | 2019-11-29 | 2020-02-16
Sea Water Intake (SWI) | Electrical Test | mecanico@lekapp.cl | IT-10101 | Marine Works | Intake Tower
[6 empty] | DCS Permisives And Interlocks Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Electrical Functional Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Parameters Adjustement | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Secondary Injection Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Functional Test Protective Devices | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | DCS Permisives And Interlocks Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Adjustment And Test Of Protective | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Operational Range Adjustment | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Electrical Functional Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Insulation Resistance Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Electrical Functional Test (Control) | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | PT - Chek Oil Level / Test Dew Point | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | PT - Chek Alarm Control / Tripp Setting | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | PT - Inspect Bolted Electrical Connection | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | PT - Test Load TAP-Changer | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | PT - Insulation Resistance Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | PT - Perform Truns Ratio Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | PT - Perform Insulation Power Factor | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | PT - Perform Exitation Current Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | PT - Measure Resistance High Voltage | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | PT - Test Instrument Transformer | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | AT - Insulation Resistance Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | AT - Perform Truns Ratio Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | AT - Perform Insulation Power Factor | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | AT - Perform Exitation Current Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | AT - Perform Exitation Current Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | AT - Verify Secondary Voltage F-F | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Functional Test Battery Charger | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | DCS Permisives And Interlocks Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | MV Power Cable | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Charge Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Functional Test Battery Charger | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Winding Resistance Test | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Dielectric Losses | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | IPT - Apertura y Cierre de Contactactos | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | IPT - Simultaneidad de Contactos | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | IPT - Analisis de Carrera | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | IPT - Factor de Potencia | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | IPT - Punto de Rocio SF6 | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | IPT - Resistencia de Contactos | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | IPT - Estanqueidad de Gas PN | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | IPT - Funcionamiento de Calefactores | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | IPT - Umbrales de Alarma y Bloqueo | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | IPT - Resistencia Homica de Bobinas | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | IPT - Corriente de Bobinas y Motor Auxiliar | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | IPT - Verificación de Contactos | [6 empty] | 2019-11-29 | 2020-02-16
[6 empty] | Continuity Check | [6 empty] | 2019-11-29 | 2020-02-16